## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 25%
Project Task | Comment | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
NavBar |  | Dushyanta | 2019-01-31 | 2019-02-01 | 210 | 1 | 2018-11-27 | 2019-01-31 | 1 | 300 | 1 | 64
Project 2 | Category 2 | Employee 4 | 2018-12-21 | 2019-01-21 | 400 | 30 | 2018-12-21 | 2019-01-24 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2018-10-23 | 2018-12-22 | 500 | 59 | 2018-10-23 | 2019-01-04 | 0 | 500 | 0 | 71
Project 4 | Category 2 | Employee 3 | 2018-11-02 | 2018-11-12 | 250 | 10 | 2018-11-02 | 2018-11-21 | 0 | 276 | 1 | 19
Project 5 | Category 3 | Employee 2 | 2018-11-02 | 2018-12-12 | 300 | 40 | 2018-11-02 | 2018-12-18 | 0 | 310 | 0 | 46
Project 6 | Category 4 | Employee 4 | 2018-12-02 | 2018-12-12 | 500 | 10 | 2018-12-02 | 2018-12-17 | 0 | 510 | 1 | 15
Project 7 | Category 5 | Employee 1 | 2018-12-18 | 2019-01-11 | 750 | 23 | 2018-12-18 | 2019-01-16 | 0 | 790 | 0 | 28
Project 8 | Category 2 | Employee 1 | 2018-12-23 | 2019-01-31 | 450 | 38 | 2018-12-17 | 2019-01-26 | 0 | 430 | 0 | 39
project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
Project 2
Registration Page |  | Debaparna | 2019-01-31 | 2019-02-01 |  | 1
Footer |  | Divya | 2019-01-31 | 2019-02-01 |  | 1
Footer |  | Pallavi | 2019-01-31 | 2019-02-01 |  | 1
Registration Page CSS |  | Pooja | 2019-01-31 | 2019-02-01 |  | 1
About Us- Content |  | Priyanshu | 2019-01-31 | 2019-02-01 |  | 1
Login page |  | Shital | 2019-01-31 | 2019-02-01 |  | 1
SETUP

## Setup
Setup
Comment | Employee Name
Home Page | Shital
Category 2 | Divya
Category 3 | Debaparna
Category 4 | Pooja
Category 5 | Pallavi
Category 6 | Priyanshu
Category 7 | Dushyanta
PROJECTS